# Holidays Act remediation

As you know, it is complex and takes time to fix the underlying issues in our payroll systems and work through all the detailed calculations and approvals to finalise the Holidays Act remediation payments, but we are making progress.

To date, we have made interim or final remediation payments to around 80% of our current employees, and we are working hard on the remainder. We want to complete this work as soon as possible,

Because there are so many variables and unknowns, it’s not possible to set payment dates accurately very far ahead. Your local team will confirm the expected date for your payroll closer to payment.

We’re legally obliged to fix any incorrect leave payments going back to 1 May 2010, no matter how small.

Not everyone is due to receive a payment – some people have been paid correctly for their leave.

Each payroll project is remediating current employees first, then former employees.

Payments to former employees are planned to start soon. Once the first payments to former employees have been successfully completed, we will be able to plan the timing of future similar payments with greater certainty. In the meantime, all former employees are encouraged to register on the portal, including any legal representatives for the estates of former employees.

Here’s a summary of estimated timings for current and former employees, as at 30 September 2025.

| District/Project | Current Employees – Estimated Remediation Date |
| --- | --- |
| Canterbury / West Coast | October 2025 |
| Mid Central | March 2026 |
| Lakes | May 2026 |
| Whanganui | May 2026 |
| Tairāwhiti | Completed August 2025 |
| Waikato | Interim completed June 2025. Full payment March 2026 |
| Southern | Completed June 2025 |
| Capital and Coast | Completed May 2025 |
| Hutt Valley | Completed April 2025 |
| Northland | Interim completed April 2025. Full payment February 2026 tbc |
| Nelson / Marlborough | Completed April 2025 |
| Wairarapa | Completed March 2025 |
| Bay of Plenty | Interim completed December 2024. Full payment November 2025 |
| Taranaki | Completed December 2024 |
| South Canterbury | Interim completed December 2024. Full payment October 2025 |
| Hawke’s Bay | Interim completed November 2024. Full payment October 2025 |
| Auckland Metro | Completed July /September 2023 |
| Transferred employees | TBC |

| District/Project | Former Employees – Estimated Start Date of Payments |
| --- | --- |
| Taranaki | October 2025 |
| Southern | TBC |
| Tairāwhiti | TBC |
| Auckland | November 2025 |
| Counties Manukau | November 2025 |
| Waitematā | November 2025 |
| Health Alliance; Health Partnerships; Health Source; Northern Region Alliance | November 2025 |
| Bay of Plenty | February 2026 |
| South Canterbury | February 2026 |
| Hawke’s Bay | March 2026 |
| Nelson / Marlborough | May 2026 |
| Capital and Coast | May 2026 |
| Hutt Valley | May 2026 |
| Wairarapa | May 2026 |
| Northland | May 2026 |
| Canterbury / West Coast | June 2026 |
| Mid Central | August 2026 |
| Lakes | September 2026 |
| Whanganui | September 2026 |
| Waikato | November 2026 |

## Process summary

Each payroll project team is working to correct different processes, payroll systems, time and attendance systems, and employment arrangements. Expert resources are being shared as much as possible. Nationally around 90,000 current employees and 130,000 former employees are covered by this programme.

Here’s what’s involved at every step of the way, for each payroll system:

Analyse data

- check data since 1 May 2010 looking at rosters, pay, leave taken, sick days, statutory holidays, overtime, allowances, call backs, extra duties, lump sum payments.

- check all MECA and Pay Equity and other settlements, and the dates they came into effect during this period

- manually enter data into the system from rosters or other hard copy records as needed

- transfer data if the payroll system was changed during this period

Breaches and solutions

- independent review

- identify all the differences between what was done, and the way leave should have been calculated

- develop solutions to correct the leave calculations

Remediation calculations

- test and retest the solutions

- make sure results are consistent with the Holidays Act, the 2020 Memorandum of Understanding with the Labour Inspectorate and unions, other decisions already taken, and the relevant employment agreements

- calculate the difference between what was paid, and what should have been paid, for all leave taken by each employee

- each incorrect leave payment affects all the subsequent payments to that employee

- each payroll project team ends up with millions of rows of data to be checked

Rectification configuration

- highly complex work to rebuild, patch, test and reconfigure the payroll system and processes to comply with the Holidays Act

- communications and training in updated processes, to ensure future leave payments will be accurate.

Quality assurance

- District Steering Committee reviews and checks

- Health NZ project team reviews and checks

- National Programme Management Office reviews and checks

- two independent quality assurance reviews of all decisions and calculations

- each of these reviews can identify changes needed, meaning more work to develop and test solutions, and potentially redoing some of the steps already taken

Funds request

- apply to Ministry of Health and Treasury to approve funds for payment

- validate, justify or rework data as needed

Go live

- tests and dress rehearsals

- the rectified payroll system goes live, so future payments will comply with the Holidays Act

Payment

- tests and dress rehearsals

- any leave payments owing are paid to current employees in that payroll

- detailed statements are available for employees about how any payments to them were calculated, and a help team responds to payment queries.

Here’s a progress summary chart that shows which steps in the process each payroll has completed / is working on / has planned.

Payments to current employees

| As at 30 Sept 2025 | Analyse data | Breaches and solutions | Remediation calculations | Rectification configuration | Quality assurance | Funds request | Go live | Payment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Auckland | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Bay of Plenty | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓* | ✓* |
| Canterbury | ✓ | ✓ | ✓ | ✓ | o |  |  |  |
| Capital Coast | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Counties Manukau | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Hawke’s Bay | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓* | ✓* |
| Hutt Valley | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Lakes | ✓ | o |  |  |  |  |  |  |
| MidCentral | ✓ | ✓ | o | o |  |  |  |  |
| Nelson Marlborough | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Northland | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓* | ✓* |
| South Canterbury | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓* | ✓* |
| Southern | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Tairāwhiti | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Taranaki | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Waikato | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓* | ✓* |
| Wairarapa | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Waitematā | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| West Coast | ✓ | ✓ | ✓ | ✓ | o |  |  |  |
| Whanganui | ✓ | ✓ | o |  |  |  |  |  |
| Health Alliance | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Health Partnerships | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Health Source | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |
| Northern Region Alliance | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ | ✓ |

| ✓ | = completed |
| --- | --- |
| o | = in progress |
|  | = planned |

*An interim payment was made in several payrolls, with remaining amounts covering issues such as ‘Otherwise Working Days (OWD)’ to be paid separately.

Payments to former employees

If you worked at a former District Health Board, or Health Alliance, Health Partnerships, Health Source or Northern Region Alliance at any time since 1 May 2010, and you no longer work there or your employee record was ‘terminated’ in the payroll system, please register on the national portal for Holidays Act remediation for our former employees. There is also information on the portal about how to register for those with power of attorney or representing the estates of deceased former employees.

To register, former employees will need to complete the ‘Getting started’ section in the portal. Closer to payment time, you will be asked to provide additional details through the portal – this information is needed before we can make a payment to you.

You may also be a ‘former’ employee if you moved to a different location or role within Health NZ after it was formed on 1 July 2022.

The secure portal will be a single point of contact and source of information for former employees nationwide. The portal has been independently assessed by security experts, to ensure your information remains private and secure.

Former employees can register here: https://remediate.tewhatuora.govt.nz. Note: If you normally use a private VPN service on your computer, you may need to turn this off to access the portal.

If you are not a former employee, you don’t need to register – your local payroll team already has your bank account and other details.

When it comes to paying former employees, rectification configuration isn’t needed as the payroll system will already comply with the Holidays Act. Remediation calculations will need to cover all the same factors as for current employees. There is an additional requirement - to analyse how termination payments were calculated and correct any incorrect payments. This is likely to involve developing an additional model to recalculate termination pays for that payroll.

Payments will be scheduled in tranches by each payroll when they are ready.

| As at 30 Sept 2025 | Current employees paid | Analyse former employee data | Breaches and solutions | Remediation calculations | Quality assurance | Funds request | Go live | Payment |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Auckland | ✓ | ✓ | ✓ | o | o |  |  |  |
| Bay of Plenty | ✓* | o | o |  |  |  |  |  |
| Canterbury |  |  |  |  |  |  |  |  |
| Capital Coast | ✓ | o | o |  |  |  |  |  |
| Counties Manukau | ✓ | ✓ | ✓ | o | o |  |  |  |
| Hawke’s Bay | ✓* | o | o | o |  |  |  |  |
| Hutt Valley | ✓ | o | o |  |  |  |  |  |
| Lakes |  |  |  |  |  |  |  |  |
| MidCentral |  |  |  |  |  |  |  |  |
| Nelson Marlborough | ✓ | o | o |  |  |  |  |  |
| Northland | ✓* | o | o |  |  |  |  |  |
| South Canterbury | ✓* | o | o | o |  |  |  |  |
| Southern | ✓ | o | o | o | o |  |  |  |
| Tairāwhiti | ✓ | o | o | o |  |  |  |  |
| Taranaki | ✓ | ✓ | ✓ | ✓ | o | o |  |  |
| Waikato | ✓* | o | o |  |  |  |  |  |
| Wairarapa | ✓ | o | o |  |  |  |  |  |
| Waitematā | ✓ | ✓ | ✓ | o | o |  |  |  |
| West Coast |  |  |  |  |  |  |  |  |
| Whanganui |  |  |  |  |  |  |  |  |
| Health Alliance | ✓ | ✓ | ✓ | o | o |  |  |  |
| Health Partnerships | ✓ | ✓ | ✓ | o | o |  |  |  |
| Health Source | ✓ | ✓ | ✓ | o | o |  |  |  |
| Northern Region Alliance | ✓ | ✓ | ✓ | o | o |  |  |  |

| ✓ | = completed |
| --- | --- |
| o | = in progress |
|  | = planned |

*An interim payment was made in several payrolls, with remaining amounts covering issues such as ‘Otherwise Working Days (OWD)’ to be paid separately.